Deliverable 2: Project planning

Planning of the entire execution of the TFG. Students should provide a description of the project phases and the resources and requirements associated with each one. Some of the scheduling tools described in the module should be used. The document can be no longer than 5 pages

1. Planning and scheduling

The aim of this document is to present the tasks and stages of the project and how are they going to be planned and scheduled so the project meets its objectives within the given deadlines.

Because we depend on the different stages of the project to work, this planning might be updated as the project progresses, perhaps because a part took longer to develop than expected or (luckily) less.

2. Task description

Introduction to the problem

Study past research papers related to the problem to gain some background on the project, this includes the following topics:

- The use GNSS data as a solar flare meter. Some research papers about this topic were discussed in the State of the Art section, most of them written by the director, Manuel Hernández-Pajaras
- Solar and stellar bursts and their effect on Earth’s ionosphere. The aforementioned papers give a brief introduction to the topic, although others can be found [Ionospheric effects of solar flares] that treat the topic with more depth.

GEP

This is one of the most challenging problems of the project. Before developing the necessary algorithms to be able to perform this without knowing the source of the flare, a study should be done with the already existing algorithms.

Feasibility of the detection of flares from far-away stars

This is one of the most challenging problems of the project. Before developing the necessary algorithms to be able to perform this without knowing the source of the flare, a study should be done with the already existing algorithms.

To do this, we will use open-source data from missions like Swift or Fermi (satellites that are able to detect flares or burst) and see if there is any correlation between that data and the results given by the algorithms that detect solar flares.
Detection of solar flares with no information about the source

This task will be done in parallel to the previous one. The current algorithms are able to, knowing the position of the sun, study if any flares have had an effect on the ionosphere, detectable by the satellites belonging to GNSS.

We aim to do the same, but assuming we don’t have any information about the position of the Sun relative to the Earth. This is an important task for the project, because it will be necessary when expanding it to far-away stars, of which we ignore the location.

Writing the report

This task will be done in parallel to the rest. As we perform the other tasks a memory of the project should be written that will give a detailed explanation of all the phases, the methodology and development of the solutions, problems or obstacles that might have appeared, and the final results of each of the phases.

3 Time table

4 Scheduling: Gantt chart

The development of the project will span between 4 or 5 months, taking into consideration that it started mid-February and the lectures are scheduled for the first week of July.

In this section we aim to give a brief description of the area of interest of the project and present which actors are going to be involved in its development.

5 Gantt chart

In this section we aim to give a brief description of the area of interest of the project and present which actors are going to be involved in its development.